## Instructions
Learning Objectives
The goal of this document is to practice goal setting and production tracking. Students must clearly (and honestly) communicate their goals and roles to everyone on the team. This helps to set the expectation within the team, and better facilitates the setting of realistic goals for the project. | Tasks need to be listed out, with estimations on the amount of time required to complete them. The estimation could come from the person taking ownership of said tasks. Otherwise there should be a general consensus of how long a specific task should take. The sequence and priority of tasks need to be carefully considered. The amount of time each team has to complete the project is fixed and known from the start. Some tasks require the completion of others to be completed before they can be started. Some tasks come with varying importance, risks/rewards and difficulty. Discerning the extent of each trait can help guide the team on the priorty and sequence of things to be done. Feedback for the grading of this document and the rubrics can be found on the "Grading" page.
Brief
You need to fill up 3 sections in this document : Main, Goals, Backlog
Main
This section contains the top level view of the project. It should show all essential information of the project at a glance, like the team composition and a summary on work progress. There are formulas implemented on the "Backlog" tab to automate the updating of columns D-H. Should the given formulaes not work, students will need either need to fix/update the formulas, or input the raw values themselves. | As much as possible, try to divide the workload evenly and/or within the means of the team members. Note that this module focuses on developing both production and technical skills. More than 50% of the work done per individual should be coding related. Contributing less than 50% of overall work done in code can lead to a penalty on the final grade.
Fill in the following:
<team name> | The name of the team. Overwrite the <team name> text with the name of the team.
<project name> | Name of the project. Overwrite the <project name> text with the name of the project
<project brief> | A brief description on what the project is about. This should help the instructor easily identify which project in the class is yours, without the need to reference anything else. You may use the brief description written in the SRS.
Project Status | Refer to the "ProjectStatus" tab of this document to select the appropriate status. This will need to be updated for each submission of this document.
Comments | If you have anything you wish to add with regards to your
Student Names | Be sure that there should be no ambiguity with your names within the team. There have been teams with members with the same first name, and they only used their first names to no avail.
Student DigiPen E-mail | This needs to be accurate as it will be used to uniquely identify each student. It will greatly help lecturers contact students too.
Average Weekly Hours | Each student needs to declare the number of hours per week that they will work on the project. Every student has their own degree of ability to cope with this class and the other classes. An honest and realistic answer to this needs to be set, to better control the scope of the project and by extension, the scope of work needed to be done per individual.
Number of weeks | Number of weeks this plan is scheduled for.
Goals
Students should set personal development goals within this project. Common interview questions to job applicants: - Describe an experience of dealing a difficult problem and how you overcame it. - What is your specialty? - Where do your interests lie? - What have you done before? | Make the best use of the time spent on projects to develop your own answers to these questions. Each student in the team will fill in their goals and write a summary on the scope of work that the student is in charge of. Naturally not all tasks will help an individual work towards their goal. Those tasks may be essential for the project. Effort and initiative will be required to better align tasks with goals. Do consider the goals of team members when coming up with and assigning tasks.
Backlog
This section should contain all conceivable tasks required for the project. Teams should brainstorm to exhaustively populate this list with tasks they may deem relevant. A good way to do this is via a top down approach, starting with "Epics" that define a broad genre or feature required. Then within each epic, think about that tasks required to achieve said epic. Then comes setting priorities, sequencing and assigning of tasks. | The backlog also tracks the progress of the project, recording the various states of progress for each task. Tasks can be added based on new ideas and requirements within the project after the initial submission. The backlog should work for you, not against you. For each task in the backlog, it is important to fill up the following details:
Completion | There are 3 options to choose from, refer to the "TaskStatus" tab for more details. The team will need to come to a consensus as to what "Completed" means. Case Study: A member claims a task is completed, all test cases pass. Another member finds bugs with the completed task. Is the task still considered completed? Be clear on the objectives of the tasks. Write it in the task description. So long that is fulfilled, the task is done. We cannot foresee all issues that will arise, so create new tasks to handle them.
Priority | There are 4 options to choose from, refer to the "Priorities" tab for more details. You need to be strict and honest on the priorities for tasks. The best of plans can be laid out, but things do not always go to plan. You will need to be clear on what the most important tasks are when that time comes.
Epic | This is the broad genre definition of a requirement for your project. Come up with high level features that are required for your project, then come up with smaller tasks.
Task | Task title. Be as specific and concise as possible.
Description | A task title might not adequately address what is required of a task. Use this section to add more details, especially for tasks which seem to be complicated. If it takes a lot to describe a task, that task should be probably broken down into smaller tasks. If the task title is clear enough, there is no need for a description.
Assignee | The name of the team member in charge of the task. It is important to be clear as to who is in charge of each tasks. The assignment can be changed as the project progresses to adapt to the situation.
Type | Refer to "TaskTypes" tab for more details. All of you are on the computer science track, so the bulk of your work done should be code related. At least 50% of work done by each student needs to be coding related, either as "Code" or "Bug fixes". This is key to adding value to your degree related experience.
Estimation | The number of hours that the task requires for completion. Note that each member of the team would have indicated the number of hours they can commit to the project a week. Use this estimation to gauge whether your tasks and project are within your budget of time.
Planned Completion Date | Every task needs a deadline. This will help with sequence planning and to gauge if you are on track to finish your project on time.

## Goals
Name | Goal/s - What do you wish to accomplish in this project? - What do you want to showcase with your work? | Work Scope Summary - Features you are working on
Jeryl Teo Jiele | My goal is to create an engaging game that is enjoyable to play. I want to showcase my ability to create a game with solid mechanics, interesting gameplay, and attention to detail. | Platform Battle room Combat & Gameplay mechanics Storyboard Design assets
Yong Yip Han, Edgar | I wish to learn more about Level Design, game balancing. Implementing cool boss attacks, player interaction I hope i can implement a decent physics systems using knowledge from previous trimester | Basic Systems features (State, Assets manager) Player vs boss (Platform Room) Physics System
Yeo Zhao Quan Xavier | I hope to complete the game without any problems, with application of the lessons i learnt in this trimester. Battle concept | Combat Inventory Manager Audio Manager
Ding Xirui | I wish to expand my knowledge in game development and improve at designing and debugging. I hope to learn from one another and complete the game entirely. | Increase Game difficulty Rest Room Mechanics INGame Upgrades
Mah Ming Qian Michael | I want to improve my coding skills. I hope to learn more about game design, creating interesting in-game events. | Main Menu External file save, load Rest Room Event Room

## Main
SushiWorld
SushiTale
Sushi Tale, a role-playing game that takes you on a culinary adventure through a fantasy world filled with delicious sushi dishes. The game will be a single-player, turn-based RPG that takes place on a randomly generated map. The player will control a character who must explore the map, defeat enemies, and collect ingredients to prepare for the final boss battle.
Project Status | GREEN
Comments
Hours
Student Name | Student DigiPen e-mail | Average Committed Weekly Hours | Done | In Progress | Not Started | Total Workload | Code / Bugs Completed
Jeryl Teo Jiele | t.jeryljiele@digipen.edu | 8 | 14 | 9 | 19 | 42 | 2
Yong Yip Han, Edgar | y.yiphanedgar@digipen.edu | 8 | 15 | 7 | 24 | 46 | 4
Yeo Zhao Quan Xavier | z.yeo@digipen.edu | 8 | 6 | 13 | 22 | 41 | 4
Ding Xirui | ding.x@digipen.edu | 8 | 13 | 6 | 26 | 45 | 0
Mah Ming Qian Michael | m.mah@digipen.edu | 8 | 0 | 2 | 41 | 43 | 0
| Team Totals : | 40 | 48 | 37 | 132 | 217 | 0
Budget Summary | Column1
Total Hours Per Week | 40
Number of weeks | 8
Total time budget | 320
Workload | Must have | Should Have | Could have | Task Total
Level | 8 | 4 | 0 | 12
Art | 4 | 0 | 2 | 6
Audio | 0 | 0 | 4 | 4
Code | 48 | 76 | 4 | 128
Bug Fix | 0 | 14 | 0 | 14
Admin | 53 | 0 | 0 | 53
Priority Total | 113 | 94 | 10

## Backlog
Completion | Priority | Epic | Task | Task Description | Assignee | Type | Estimation (Hours) | Planned Completion Date
Completed | Must Have | System | Game State Manager | Allow for transition between states | Yong Yip Han, Edgar | Code | 4 | 2023-01-09
In Progress | Must Have | System | Assets Manager | Help Load fonts and textures | Yong Yip Han, Edgar | Code | 4 | 2023-02-08
In Progress | Must Have | System | Mesh Creator | Presets for mesh, with different colors (run time generated) | Yong Yip Han, Edgar | Code | 3 | 2023-01-13
In Progress | Should Have | System | Animation Loader | Import sprite sheets to be used for animation | Jeryl Teo Jiele | Code | 5 | 2023-02-08
Not Started | Should Have | System | Audio Manager | Load audio and use it throughout game | Yeo Zhao Quan Xavier | Code | 5 | 2023-03-01
Not Started | Must Have | System | Collision | Player and Environment Collision | Yong Yip Han, Edgar | Code | 5 | 2023-02-15
In Progress | Must Have | Helper Features | Main Menu | Navigation to different states when program starts | Mah Ming Qian Michael | Code | 2 | 2023-02-10
Not Started | Should Have | GamePlay | Pause Screen | Allow Player to pause game | Mah Ming Qian Michael | Code | 2 | 2023-02-13
Not Started | Must Have | Helper Features | Options Menu | Control audio / sfx levels | Mah Ming Qian Michael | Code | 2 | 2023-02-10
Not Started | Should Have | Helper Features | Load Game | Load Game file | Mah Ming Qian Michael | Code | 3 | 2023-02-17
Not Started | Should Have | Helper Features | Save Game | Save Game file | Mah Ming Qian Michael | Code | 3 | 2023-02-17
Completed | Must Have | GamePlay | Player Movement | Input for player movement | Jeryl Teo Jiele | Code | 2 | 2023-01-29
Not Started | Must Have | GamePlay | Start Map generator | Main Map for player to navigate around | Yong Yip Han, Edgar | Code | 2 | 2023-01-18
Not Started | Must Have | GamePlay | Final Boss Battle | Choose between existing battle rooms | Yeo Zhao Quan Xavier | Code | 2 | 2023-03-05
Completed | Must Have | GamePlay | Arrow Key Battle | Arrow Key Battle Room | Yeo Zhao Quan Xavier | Level | 2 | 2023-01-29
Completed | Must Have | GamePlay | Arrow Key input | Input for random arrow keys | Yeo Zhao Quan Xavier | Code | 4 | 2023-01-29
In Progress | Must Have | GamePlay | Arrow Damage | Damage calculation to enemies based off Arrow Keys input | Ding Xirui | Code | 2 | 2023-01-29
Not Started | Should Have | GamePlay | Platform Battle | Platform battle room | Yong Yip Han, Edgar | Level | 2 | 2023-02-18
Not Started | Should Have | System | Physics | Physics for player - enemy interaction, gravity.. bullets and player movement..etc | Yong Yip Han, Edgar | Code | 3 | 2023-02-18
Not Started | Should Have | GamePlay | Player Attack | Shoot Bullets | Yong Yip Han, Edgar | Code | 3 | 2023-02-18
Not Started | Should Have | GamePlay | Damage Done | Player - enemy interaciton | Jeryl Teo Jiele | Code | 4 | 2023-02-25
Not Started | Should Have | GamePlay | Boss Attack | Attack patterns for enemy | Jeryl Teo Jiele | Code | 5 | 2023-02-25
Not Started | Could Have | GamePlay | Boss Attack Animation | Flashy animation/effects for attacks | Jeryl Teo Jiele | Code | 4 | 2023-03-04
Not Started | Should Have | GamePlay | Increase Platform Room Difficulty | Limit Player Vision | Jeryl Teo Jiele | Code | 5 | 2023-03-05
Not Started | Should Have | GamePlay | Increase Platform Room Difficulty | Anti Gravity | Yong Yip Han, Edgar | Code | 5 | 2023-03-05
Not Started | Should Have | GamePlay | Increase Platform Room Difficulty | Spawn enemy mobs | Yeo Zhao Quan Xavier | Code | 5 | 2023-03-05
Not Started | Should Have | GamePlay | Increase Arrow Room Difficulty | Rotating Arrow keys | Ding Xirui | Code | 5 | 2023-03-05
Not Started | Should Have | GamePlay | Increase Arrow Room Difficulty | Unrevealed keys that reveal upon approaching | Ding Xirui | Code | 5 | 2023-03-05
Not Started | Should Have | GamePlay | Increase Arrow Room Difficulty | Arrow Keys require multiple clicks | Mah Ming Qian Michael | Code | 4 | 2023-03-05
Not Started | Should Have | GamePlay | Increase Arrow Room Difficulty | Arrow keys order starts from the back | Mah Ming Qian Michael | Code | 4 | 2023-03-05
Not Started | Must Have | GamePlay | Rest Room | Rest room state for player to heal up | Mah Ming Qian Michael | Level | 2 | 2023-02-08
Not Started | Must Have | GamePlay | Rest Room | Allowing player to heal up based off stats | Mah Ming Qian Michael | Code | 3 | 2023-02-08
Not Started | Must Have | GamePlay | Upgrading | Rest room state for player to upgrade items | Ding Xirui | Level | 2 | 2023-02-15
Not Started | Must Have | GamePlay | Upgrading | Upgrading ingredient game mechanics | Ding Xirui | Code | 5 | 2023-02-15
Not Started | Must Have | GamePlay | Shop Room | Allow Player to obtain items | Yeo Zhao Quan Xavier | Level | 2 | 2023-02-15
Not Started | Must Have | GamePlay | Inventory Manager | Inventory Manager for players' items | Yeo Zhao Quan Xavier | Code | 4 | 2023-02-15
Not Started | Must Have | GamePlay | Upgrade Manager | Manager for player's upgrades | Ding Xirui | Code | 4 | 2023-02-18
Not Started | Should Have | GamePlay | Event Room | Event room state where anything can happen | Mah Ming Qian Michael | Level | 2 | 2023-02-18
Not Started | Should Have | GamePlay | Event Room | Variety of events | Mah Ming Qian Michael | Code | 5 | 2023-02-18
Not Started | Should Have | GamePlay | Event Room | Variety of events | Ding Xirui | Code | 5 | 2023-02-18
Completed | Must Have | Sprites | Player Sprite | Player's sprite | Yong Yip Han, Edgar | Art | 1 | 2023-01-29
Not Started | Must Have | Sprites | Monsters' Sprite | Monster's sprite | Mah Ming Qian Michael | Art | 1 | 2023-02-10
Completed | Must Have | Sprites | Arrow Key Sprite | Image for every arrow key | Jeryl Teo Jiele | Art | 1 | 2023-01-29
Completed | Must Have | Sprites | Map Sprite | Image for every room in default starting map | Jeryl Teo Jiele | Art | 1 | 2023-01-29
Not Started | Could Have | Sprites | Boss attack sprite | Sprite for boss attack and animation | Yong Yip Han, Edgar | Art | 1 | 2023-02-25
Not Started | Could Have | Background | Background | Background for the game | Jeryl Teo Jiele | Art | 1 | 2023-02-11
Not Started | Could Have | Audio | Main Audio | Play throughout the game | Yeo Zhao Quan Xavier | Audio | 1 | 2023-02-27
Not Started | Could Have | Audio | Player Dmg Audio | Play when player take damage | Yeo Zhao Quan Xavier | Audio | 1 | 2023-02-27
Not Started | Could Have | Audio | Player Attack Audio | Play when player make an action | Yeo Zhao Quan Xavier | Audio | 1 | 2023-02-27
Not Started | Could Have | Audio | Game Over Audio | Play when player loses the game | Yeo Zhao Quan Xavier | Audio | 1 | 2023-02-27
In Progress | Should Have | Debug | Memory | Reduce memory usage | Jeryl Teo Jiele | Bug Fix | 4 | 2023-03-19
In Progress | Should Have | Debug | Lag | Reduce Lag | Ding Xirui | Bug Fix | 4 | 2023-03-19
In Progress | Should Have | Debug | FPS | Control FPS | Yeo Zhao Quan Xavier | Bug Fix | 3 | 2023-03-19
Not Started | Should Have | Debug | Bug | Collision not working | Yong Yip Han, Edgar | Bug Fix | 3 | 2023-03-19
Completed | Must Have | Admin | Presentation | Presentation Slides | Jeryl Teo Jiele | Admin | 10 | 2023-01-29
Completed | Must Have | Admin | SRS Report | SRS Report | Ding Xirui | Admin | 10 | 2023-02-05
Completed | Must Have | Admin | Production | Production Plan | Yong Yip Han, Edgar | Admin | 10 | 2023-02-05
Not Started | Must Have | Admin | Final Report | Final Report | Mah Ming Qian Michael | Admin | 10
In Progress | Must Have | Admin | Weekly Report | Weekly Report | Yeo Zhao Quan Xavier | Admin | 10
Completed | Must Have | Admin | Research | Research for ideas and references | Ding Xirui | Admin | 3 | 2023-01-20

## Grading
Grading
Teams start with an "A" grade. Accumulated penalties will be applied to lower the grade. Teams do not need to fill this page.
Penalties | Penalty Range | Penalty Given | Feedback
Tasks that are "Must Have" have missing data. | -1 to -4
Assigned tasks leads to member/s exceeding their time budget. Example. Assignee commits 10 hours a week for 6 weeks. 61 hours of work were assigned. Penalty given. | -2 per offending member
Tasks are too vague. Tasks title and/or description does not sufficiently inform the assignee the scope of work required. | -1 per 10% of tasks
Tasks too large. Requires more than a week of the assignee's commitment. Break it down into smaller tasks. Should a task require more than a week of work, a team can be set back significantly if that task is not completed by the allocated date. Penalty is high to discourage this. | -1 per offending task
Goals page not filled up/ not filled up properly. | -2 per offending member
Missing data on the main page. | -1 per missing data field.
Workload not well distributed. Difference between workloads between two or more members is greater than 20% of the workload done by the member with a smaller workload. | -1 to -4
Priorities and/or sequences of tasks work against the completion of the project. Includes but not limited to: - "Must Have" features left to the end of the production pipeline - Key features not labelled as "Must Have" - Tasks with pre-requisites are planned to be completed without the pre-requisites completed. | -1 to -4
| Total Penalty | 0
Final Grade

## Priorities
Priorities | Brief
Must Have | Critical, cannot do without
Should Have | Important to the project but not vital
Could Have | Nice to have
Won't Have | Would not contribute to your project, can do without

## TaskTypes
Task Types | Description & Requirements | Requirements
Level | For tasks related to creating levels for the project. Ideally done without hardcoding all objects in the level within code. | @Must have a beginning and an end @Meaningful choices for the player to make @Clear objective
Art | For tasks related to creating visual art assets for the project. This includes fonts. Fonts : There are some license free fonts allowed for use. Refer to forum post. This should be kept to a minimum for RTIS and IMGD students. | @Refer to the EULA that you signed at the start of the semester @Do not use existing art assets even if they are "license free" @Tools used in the generation of art assets must be license and cost free
Audio | For tasks related to finding, creating and/or getting audio assets into the project. There are audio assets provided by the school via MetaDigger. Refer to forum post. The tasks related to coding an audio system to play audio assets should be under "Code". The audio system is a coded feature. | @Refer to the EULA that you signed at the start of the semester @Usage of existing audio assets allowed only for those found in the school's MetaDigger @Do not use external existing audio assets even if they are "license free", provided for or generated by tools @Recording your own audio, editting it with a free tool and using that asset is allowed
Code | For tasks related to feature implementation and code integration. Hardcoding levels and content for the game does not fall under this category. That would be under the task type of "Level" | @Feature functions as described and intended @No crashes, warnings, errors from implementation @Does not break existing features. If it does, those breaks should be fixed for this task to be done
Bug Fix | For tasks related to fixing bugs that have been detected. Debugging is expected to be done during coding and development, but not all bugs would get detected during that phase. | @Symptoms identified with bugs gone @No crashes, warnings, errors from implementation @Does not break existing features. If it does, those breaks should be fixed for this task to be done
Admin | For administrative tasks like: @Presentation materials @SRS and production documents @Marketing materials

## TaskGrading (hidden)
Brief | Grades here denote the perceived complexity of the task by the lecturer. This perception is based on expectations of the students' education so far from this semester. Estimated work hours stated here reflect what the lecturer perceives as the time required to complete by the student based on the education received so far.
Grade | Description | Estimated Work Hours
A | An advance task that requires self-study, using techniques not taught in class, a great challenge for the student at this current stage of education. | 8
B | A task within the ability expected of students, an advance application and usage of what has been taught. Students should be able to complete | 5
C | A basic task that the student should be able to complete in 2 hours or less. | 2
F | Unable to discern what the task is. Task is poorly defined. Task is too big to be useful. | 0

## TaskStatus
Status | Description
Not Started | Task is/will be completed and in the final product
In Progress | Being worked on. Includes testing and debugging
Completed | Done, in working order.

## ProjectStatus
Colour | Description
RED | More than a week behind. Having multiple difficulties. Some problems impeding or halting progress. Need help. | If your Team is experiencing any problems, do write it down in the comments below your project status
YELLOW | One week Behind
GREEN | Ahead or on time